1

DFID/FEDERATION INSTITUTIONAL STRATEGIC PARTNERSHIP - III

DG ECHO / FEDERATION CAPACITY BUILDING PROGRAMME 2009/10

[image: image1.jpg]



JOINT IFRC/DG ECHO/DFID/BRITISH RC - REVIEW MISSION 

TO 

SOUTHERN AFRICA (ZONE) AND MOZAMBIQUE

25-29 May, 2009
Team members: 

· Tiziana Bonzon, DM Programme Coordinator, IFRC
· John Roche, Operations Coordinator for Africa, IFRC

· Anna Bergeot, Policy Coordinator, DG ECHO, Brussels

· Denis Heidebroek, DG ECHO, Nairobi Sector Support Team

· Jack Campbell, DRR Adviser, DFID 

· Igor Hodson, Humanitarian Policy Officer, British RC

Table of Contents

1. Introduction

2. Findings and recommendations
Methodology and joint framework for analysis

· Disaster Preparedness and Disaster Risk Reduction

· Disaster Response 

· Early warning / Information management, 

· WASH, Shelter and Recovery

Acknowledgements

Annexes
List of acronyms and abbreviations
1. Introduction
The DG ECHO Capacity Building programme and the DFID IS III are essential global funding streams that contribute to the strengthening of the International Federation humanitarian preparedness capacity worldwide. These global, regional and national investments allow the organization to build, consolidate and implement disaster preparedness and risk reduction methodologies, approaches and systems, emergency preparedness for response and early recovery mechanisms and tools, a global and regional logistics set-up and supply chain as well as coordinating capacities within the Emergency Shelter Cluster. Impact of these actions is more and more noticeable at national level in good institutional capacity for disaster preparedness and risk reduction, good staff and volunteer response capacity, and increased use of beneficiary focused planning, monitoring, evaluation and accountability mechanisms (see IFRC/DFIDIS3 Annual Summary review, 2008).

The overall thrust of both grants
 is global; however a number of priority actions are carried out in given regions and countries, as listed in the respective funding application / institutional framework. 

As part of the monitoring component for both programmes, a joint DG ECHO, DFID, British RC and IFRC review was carried out 25-29 May, 2009 to South Africa and Mozambique.

The scope of this review was threefold:
· To review IFRC secretariat, zonal and national society field performance for 2008-09 under the DFID IS framework: reporting on achieved results, documenting any challenges and constraints encountered which may have hindered programme delivery, as well as any emerging opportunities which should be taken into account during the future management of support

· To review IFRC field performance under the ECHO- supported Capacity Building programme. Specifically the review aims to assess progress in Disaster Risk Reduction and Disaster Preparedness, Water and Sanitation, and IDRL components. Overall effectiveness of the institutional strengthening supported through previous thematic investments at Global, Regional and National levels will also be assessed.  

· To identify the level of complementarities between these two global funding streams and to what extent they both contribute to achieving programmatic donor harmonization, particularly, but not exclusively, in relation to recovery and sheltering programming.

This report aims at highlighting the main findings within the given framework for analysis and provides a number of recommendations, more strategic in nature rather than technical, for consideration by all partners. 

Findings are the result of discussions with programme managers from the Zone and Country offices as well as from the National Society (headquarters and branch levels) and some external stakeholders (e.g. INGC). To complement the information gathered during the visit, this report builds on previous reports and evaluations which were part of the desk review (see list of consulted documents in annex)
. Background information about the two partnerships and the programmatic / geographical focus of this review, can be found in the Terms of Reference which are part of the annexes. 

2. Findings
Methodology and joint framework for analysis

The areas of enquiry and respective criteria identified in the section below are obtained from the “Characteristics of a well-prepared National Society” (WPNS) and from the indicators developed to monitor the DFID IS III and the DG ECHO Capacity Building programme. The methodology followed for this field review used these criteria not only to guide the interviews and collection of secondary information but mainly as comparative measures to assess regional and national capacities. The methodology and visit time-frame did not allow for a deep firsthand evaluation.
Disaster Preparedness and Disaster Risk Reduction
Assess capacity to reduce risks and impact of disasters on vulnerable communities through preparedness & mitigation, as well as expanded advocacy and linkages between policy and practice

Criteria

Regional/Zone level

· DM strategy is in place & zone supports NS disaster planning with clear focus on risk reduction measures 
· IFRC zone office supports assessments through development and promotion of tools and methodologies (VCA, WPNS, Emergency preparedness guidelines, etc)
· IFRC promotes updated contingency planning tools and supports training activities at regional level as well as national.

· Shared learning between the NS in the Zone

1. Since its establishment in 2008, the Zone has focused on organisational change as a starting point for improving DM. It has therefore been putting strong emphasis onto regional and national planning as well as self-assessment. The development of a five-year “DM master plan” with 7 NSs from the region, which led to the “Zambezi river initiative” (see more under point 2.), had as pre-condition the completion of the WPNS process to identify gaps and needs and feed those into the master plan. WPNS phase II was therefore carried out in 2008 by six national societies – Lesotho, Malawi, Mozambique, Namibia, Zambia, Zimbabwe. National Societies have been using the simple checklist form at the national level, developing indicators, as an aid to understanding their own disaster preparedness status and planning needs
. 
2. As a part of the community safety and resilience framework, the International Federation through the Zone continues to promote and establish community-based early warning systems in National Societies where climate change is an emerging issue. For example, the Zone supported National Societies along the Zambezi River to set up a community-based risk reduction programme, with the aim to mitigate the impact of floods; improve livelihoods; and develop early warning systems for timely evacuations. The “Zambezi river initiative” is seen as a successful process whereby NSs committed to conduct joint planning, self-assessment and integrated programming within DM. 
Contingency plans for floods were developed by all NSs
, integrating them into the inter-agency contingency plans available in the region. The exercise was meant to allow NSs to identify capacity gaps particularly in relation to the capacity of their volunteers, equipment availability, as well as lack of epidemic control for volunteers. 
3. With regard to DRR, in Southern Africa the focus is on strengthening resilience of rural communities in wake of “triple threat”: drought, chronic food insecurity (poverty) and HIV/AIDS via mix of interventions. Main activities include: promotion of drought-resistant crops, vegetable gardens, fruit trees, small-scale irrigation, small livestock farming, and strengthening community organizational capacity. Food security projects in drought and flood prone areas focus mainly on home-based patients and orphans, and a vulnerable children’s project. The Zone encourages NS networking, peer-to-peer support, and facilitates study visits. The JMM did not give opportunity to look deeply into this area of support. It seems that the approach on the ground by volunteers to building resilience was pragmatic and adapted to a context limited longer-term resources. However this approach might not be fully in line with donor's strategies for the region and should be discussed within the framework of strategic partnership dialogues, if deemed necessary. 

4. Training in Regional Disaster Response Team (RDRT) and National Disaster Response Team (NRDT) 
has enabled National Societies from this region to undertake a consistent and comprehensive approach to VCA in disaster-prone communities. National Societies involved government departments in the VCA process as a way to share skills, expertise and competencies, and engaged in the development of disaster risk reduction plans.
5. One major challenge in this region is dealing with leadership issues at NS level, as well as ensuring that competent staff is recruited and maintained. There therefore seems to be a bottleneck in the rolling-out of some tools / training and lessons learned, reportedly because of staff turnover. Integrity was also mentioned as an important issue. Regional coaching and mentoring of national societies’ leaders is seen as a better approach to leadership training. However, the Zone office is aware that their approach has some limits, as changing mind-set is a long-term process.
6. Although PMER has been reorganized at zone level, it should be providing more support to NS in the preparation of project proposals. Indeed, NS have not gained access to DIPECHO funds lately in the region. Yet, this trend should be reverted to create a continuum between capacity building and operations financed by ECHO (and create a link between policy and practice).

National level

· Policy, strategy and planning documents are in place and effectively used 

· Links with the regional commitments such as Ouagadougou, Algiers and Johannesburg

· Damage, risk, needs and capacity assessments are carried out effectively with IFRC support and using recommended IFRC tools, whenever relevant. 

· Programme integration (e.g. with health, P&V, OD)

· NS Disaster preparedness / contingency plans are in place and up-to-date

· NS has community-based preparedness risk-reduction programmes that take into account climate adaptation

· Link with the Federation policies and principles for disaster relief and NS policies  
· Regular training and review exercises carried out for all stakeholders
· Partnerships with other agencies

· Using its auxiliary status, the NS advocates with government and other relevant partners to promote legal preparedness and risk management and NS place in national Disaster planning, legislation 

1. The criteria above were not assessed individually during the mission. They were however referred to in the discussions held with CVM and their partners. With a well structured governance system in place at national, provincial and district level, a National Society strategic plan that is aligned with the MDG and the National Poverty Eradication plan, more than 6,000 active volunteers, the society appeared to be meeting the above listed criteria in terms of planning, policy, assessment, program design and implementation. CVM appeared to be playing a critical role in disaster preparedness and risk reduction and strives to improve its systems in order to make the institution and its programs sustainable over time. Efforts go into retaining the volunteers by providing technical training, coaching, and simulation exercises.

2. CVM plays also a critical coordination role both with the authorities, by being part of a national emergency preparedness and response platform, coordinated by the INGC, the National Disaster Management Institute and its mechanisms at all levels (headquarters, province, district); and with partners, particularly with the 12 Participating National Societies (PNS) that currently support CVM with bilateral programmes. This internal coordination is ensured through annual partnership meetings, regular coordination meetings with respective country representatives. In addition, the CVM is in process of aligning funding from partners encouraging them to focus on the priorities defined by their current Strategic Plan, and to base their cooperation on a standard MoU, drafted consensually.
3. The current humanitarian consequences of climate change are being addressed by CVM. CVM demonstrated a proactive approach in seeking out relevant data on climate change, and seemed ready to think more strategically about threats and opportunities it represents. A recent study on the “Impact of Climate Change on Disaster Risk in Mozambique”, released by INGC with contribution from UNDP, opens the door to an increased advocacy role by CVM in terms of improved legislation in disaster preparedness and response, and more broadly to encourage the Government to give priority and support to intensified disaster preparedness activities, while empowering communities to face the current and future consequences of climate change. Some good practices of climate change adaptation already exist and should be further promoted. Evidence was gathered during the visit conducted by the monitoring team to the communities of Chokwe, in the province of Gaza, which received training on Climate Change Adaptation and targeted support through the DFID-funded DRR programme – phase 2 and have adapted their life-style to these new patterns of risk. Some examples of adaptation include rebuilding more water-resistant shelters by digging deeper than usually done,
 introducing drought-resistant crop and livestock, building elevated granaries, increasing risk awareness and education, establishing community-based early warning systems, etc. Overall, awareness of the threats posed by climate change amongst volunteers was detected.

4. Self-assessment, particularly in disaster preparedness, risk, vulnerability and capacity assessment are areas that CVM strongly prioritize. Not only the society uses Federation tools such as WPNS, but it aims at benchmarking its institutional capacities against other NGOs using an SGS methodology that has helped them to identify gaps and areas that need strengthening (such as conducting a consolidated audit of their programs, finding effective ways of communicating impact from their programs, etc.). The WPNS was found very useful by the society who has adapted the tool to the branch level. Other DM assessment tools such as VCA and the contingency planning guidelines have also been institutionalized and the society reported to run training and workshops on a regular basis with the branches / communities concerned
. Particular focus currently goes to addressing vulnerabilities in urban contexts, as stated by the Secretary General of CVM. These assessment processes, as already mentioned, were also a pre-condition to the establishment of the DM master plan (a regional initiative of which CVM is part) which has allowed CVM to take an integrated programming approach over a long-term period of time (five years).
5. Within the context of legal preparedness, initial preparations for an IDRL Pilot project in Mozambique took place in February/March 09. Meetings with UNICEF and UNDP, as well as with Government officials, Ministry of Foreign Affairs, Ministry of State-Administration, National Institute for Disaster Management, and the Norwegian Embassy were held, paving the way for an IDRL pilot project. A follow-up visit by the regional IDRL delegate is planned in September to either organise the official launch of the pilot project with the government or adopt a more project start-up policy (i.e. getting some preliminary research done prior to the official constitution of a governmental task force) to ensure that some real progress is reported in the coming months.   
6.  Expectations in PMER are often unrealistic at national level. Although the International Federation has been improving its performance management systems and has established some capacity at Zone level, this is not always (or not yet!) reflected at national level or down to districts. One reason for this seems to be related to the capacities of the Zone PMER unit itself, which the mission found to be minimal and stretched over many different tasks. Recruitment of PMER officers at national level is also a challenge and PMER is now added on top of many other tasks that programme managers have to carry out. The consequence is that monitoring, evaluation procedures as well as reporting remain weak. Existing Federation tools and methodologies (log frames, work-plans, reporting templates, etc.) should be adapted and simplified to the regional / national context in order to promote a more realistic collection of data and analysis of progress. In the case of CVM this should for instance take into account limitations in terms of transport, literacy, etc. 
7. A challenge for CVM is the need to mainstream the several projects (too many) run by the NS, especially in health and DM. The burden of project-based financial management, monitoring and reporting is excessive. There is obviously a discrepancy between donors’ requirements and RC volunteers’ (reporting) capacities. The new PMER unit expresses need for technical assistance from their partners in order to improve quality in a more systematic way. Establishing an operational alliance with all partners involved might be a solution, which CVM is currently considering.
8. CVM continues to face the challenge of finding ways to support its core costs. This affects business at all levels, but was most starkly evident at the branch level in Chokwe, where there were not even funds available to pay the electricity bill and meetings were conducted in the dark.  One third of CVM core costs are covered through local income-generation activities. This effort should be commended as this is time consuming and requires specific skills. In 2008, the Mozambique government provided for the first time some financial support to CVM to cover for its running costs. This is the sign that the government recognises CVM as a valuable partner. There was not opportunity to verify the extent to which support for fundraising capacity building had come from IFRC Zone/HQ.
9. Finally, there is a need for IFRC country delegate(s) to play a pro-active role (as the main interface between the zone office and the NS), in the way DM capacity building needs from the NS & resources, from Zone Office/HQ are identified and matched. The Federation should better define what services are to be delivered at country level and appropriately resource this.

	Recommendations
	Who

	DP/DRR Planning and programming
	

	A bottom-up approach in longer-term planning is clearly encouraged at Zone and Country level. Nevertheless, the way in which these plans are communicated to the top through the institutional planning process (from national to zone level, from zone to global level) needs improving, and this in order to ensure that planned secretariat support reflect regional and national priorities. The team had the impression that some global initiatives and technical assistance offered to the Zone and National Societies was not necessarily demand-driven, and that peer-to-peer support and national societies networking and exchanges could address some of those needs.
	All levels

	The priorities for ‘resilience’ in the communities visited were primarily related to health and food security. The challenge for IFRC and donors is to build local level capacities in resilience-focussed work, without managing activities in artificially separate work-streams. It is recommended to continue to integrate risk reduction programming within the broader disaster management cycle and ensure that funding proposals reflect this approach at all levels. Donors should be encouraged, within their specific mandates and terms of financing decisions, to support a mix of interventions that allow building sustainable capacities.
	All levels / donors

	From a DM program management perspective, the Zone and the national societies in the region appear to be adopting an integrated approach to addressing risks and vulnerabilities. This means that disaster preparedness measures are linked to food security, water and sanitation and health care (incl. HIV/AIDS) interventions at all levels. The International Federation, and in particular the Zone and national societies concerned, should however clarify the linkages between disaster risk reduction, food security, HIV/AIDS (where appropriate), and early recovery and how a mix of interventions in these sectors contribute to increased community resilience. Program design should also clarify the threshold where disaster management is not longer related to emergency aid but to chronic needs.
	All levels

	At the national level there seemed little evidence or incentive for HIV/AIDS staff to plan together with DM/DRR staff. In line with the above finding, it is recommended that planning at national level reflects the same integrated approach.
	National level / CVM

	Further investment in human resources and training on planning, monitoring and evaluation at national level is needed. In addition better balance between the use of resources to revise existing tools and the dissemination of these tools (training) should be sought. Partners should also acknowledge these challenges and agree on performance frameworks that take existing limitations into account while investing into PMER national capacities. 
	Global / Zone / National / donors

	Organisational development, advocacy and standards
	

	Regional coaching and mentoring of national societies’ leaders is seen as a better approach to leadership training. It is recommended that OD work in this area acknowledges and addresses the limitations of training provided and explores other avenues to ensure that knowledge and good practices are promoted. 
	Global / Zone

	Sustainability of the institutional capacity building of the national society remains an area of concern. This has to be strengthened to ensure that the institution and the programmes it runs are sustainable even after external funding ends. National and regional strategic plans should more clearly integrate OD components. The capacity of a NS to run DM programs should be carefully appraised at all levels (particularly branch level and closer to the communities).
	National / Zone

	At the same time, funding streams should more systematically consider supporting institutional capacity building at national level (income generation, financial management, volunteer management, PMER systems, fundraising, etc.). DREF is seen as an appropriate channel to boost local level capacity but needs to be complemented by other funding mechanisms                        .
	All levels / donors

	CVM have only partially achieved alignment of funding from PNSs, and the demands of this complex, projectised funding base poses real challenges for CVM in terms of planning, reporting and ultimately on their capacity to deliver. It is recommended that technical assistance and support is provided to the newly created PMER unit which aims at addressing these challenges. Establishing an operational alliance with all partners involved might be a solution, which CVM is currently considering.
	Zone / National / CVM

	The national society should increasingly use its auxiliary role to advocate for humanitarian issues of concern (i.e. climate change adaptation, legal preparedness/IDRL, HIV/AIDS, DRR, humanitarian reform/cluster system, etc.) and constantly position itself with local authorities at all levels, explaining the comparative advantage of the Red Cross vis-à-vis other humanitarian organizations. Increased support and advice should be requested from the Zone office, where a new “humanitarian diplomacy” unit has been established aiming exactly at helping national societies within the region to play a stronger role within their respective countries, particularly with regard to clarifying and deepening the auxiliary status.
	Zone / National

	The national society and the Zone should systematically disseminate existing standards and policies (PSEXA, Code of Conduct in disaster relief, etc.) not only within the humanitarian community but also to local authorities. This is to raise and maintain awareness, and avoid that similar work is undertaken in parallel. 
	Zone / National


Disaster Response
Assess level of capacity to respond to the effects of disasters and to provide appropriate services to the most vulnerable throughout the disaster cycle

Criteria

Regional/Zone level

· Surge capacity available to support NS response in all aspects of DM

· IFRC makes DREF funds available as required and supports resource mobilization

· RLU or other Federation regional hubs ensure efficient and cost effective provision of resources

· IFRC coordinates disaster response in different sectors from PNS and other sources
· IFRC ensures an accurate needs assessment and response mechanism using standard tools and guidelines. Regional Emergency Appeals contain plans of actions based on properly assessed needs and considering recovery and risk reduction issues
· IFRC mobilises and manages relevant teams (FACT, RDRT, ERUs etc)drawn from competent and well trained staff and ensures coordination between them
1. The Southern Africa region saw a major shift in its patterns of risk and vulnerabilities, from post-war to those prompted by natural disasters (exacerbated by climate change), food insecurity and health emergencies such as HIV/AID, epidemics, etc. This meant dealing with national societies and communities who lacked exposure and experience in responding to these new challenges and the complexity of different but often inter-linked vulnerabilities. 
2. Nevertheless capacity to respond has been built over time through for instance the establishment of the RDRT mechanism, pre-positioning of regional and national stocks (procured from Dubai RLU), and the development of MoU among NSs for the use of stocks across borders. Experience has also been gained by the deployment of international tools such as ERUs whereby the NSs benefited from transfer of knowledge and expertise (i.e. water and sanitation) that can now be used nationally and within the region. One of the major challenges today is the pace at which floods are followed by droughts stretching national societies’ capacities and leaving communities with little time to recover, hence the need to explore ways of coping while preparing for the next disaster.
3. Currently the SA Zone provides logistics support through a Zonal Logistics coordinator, has regional emergency stock in Harare (details available) as well as vehicles. As part of the current sub regional stock strategy the Zone together with the Logistics department in Geneva are assessing where it is most suitable to have a regional stock (if Harare or Joburg or other location).
4. In the meantime, the global shelter program has already supported the prepositioning of 4000 shelter kits stock in Harare and 5000 units in Nairobi to cover South and East Africa Regions. Zambia, Angola and Namibia received shelter kits in response to their respective floods operations. Water and Sanitation Kits are already positioned in Harare for use in the zone and have been recently deployed for cholera (Zimbabwe) and floods response (Namibia) operations. Kits are replenished from the resultant emergency appeals. 
5. This is a region that has often required effective use of regional and international surge capacity tools such as RDRT, FACT and ERUs. In the past two years support was provided to several of its National Societies emergency response work, by welcoming international emergency response teams (ERUs) to Mozambique & Madagascar (2007),  Zimbabwe (2008/09 – deployments ending in April) and Namibia (April / May 2009) for a total of 15 deployments. Support was given in the form of logistics, IT&Telecom, relief, health and water & sanitation. To some extent (in health for instance) support was given to both the National Society as well as the local health authorities, notably in Vilanculos, Mozambique, where a local hospital was assisted after the destruction of its premises and international staff from Norway and Canada assisted, as well as in Zimbabwe, where expatriates ‘shadowed’ and supported Zimbabwe Red Cross (ZRCS) and MoH staff during their cholera operation throughout the country. The operation in Zimbabwe was a unique opportunity to combine the revamped Mass Sanitation Module ERU (MSM) with the basic Health Care ERU and have them supported by two Water providing modules (one M15 and one M40).  The health focus was twofold – supporting Zimbabwe RC and MoH staff in cholera case management while at the same time broadly engaging in sanitation and health promotion activities through ZRCS community based approach. 
6. Country-level response capacity has been strengthened in all three aforementioned countries through engaging National Society staff (i.e. Mozambique, Zimbabwe and right now Namibian RC staff) in the ERU work for several months, leaving the staff with heightened relief, logistics, health and water and sanitation skills and a better understanding of the DM linkages within the organisation. 
7. The Angola floods operation also experienced the deployment of the British RC Household Economic Security (HES) module in April 2009. The HES is part of the Federation Early Recovery Surge Capacity and has a MoU giving it auxiliary status to our global tools (FACT, RDRT, ERU).
National level

· NS has sufficient number of staff/volunteers with updated skills in assessment and risk analysis, first aid, water and sanitation, logistics and relief, and properly equipped

· Programme integration (e.g. with health, P&V, OD)NS conducts regular training related to situations of disasters (Using latest tools for NDRT, or others)

· NS response is appropriate and relief programmes reach targeted vulnerable populations

· Link with the Federation policies and principles for disaster relief and NS policies  
· NS relief programmes show increased use of quality and innovative approaches to disaster response based on needs (i.e. cash interventions, integrated sectoral approach in shelter, water & sanitation, recovery, etc.)

· NS response takes cognizance of linking relief, rehabilitation and development

· NS has access to DREF and uses it for early action on imminent crisis and early response

· NS endeavours to mobilize resources locally

· Stocks and emergency equipment are available and can be mobilized as required, either nationally or regionally
· Effective coordination with all stakeholders
· Quality of response is monitored and evaluated.
1. The meetings held with CVM DM staff allowed understanding that a relatively sufficient response capacity is in place at national level to respond to small and medium-scale disasters, although the JMM was clearly not able to verify this in real time. Volunteers, organised in DM committees, appear to be available in adequate numbers to run NS programs across the country (although volunteers are never sufficient enough!), trained in appropriate skills and methodologies, contingency stocks are pre-positioned in some strategic locations across the country (for 5,000 families) and a good coordination capacity exists. Evidence of this was the way in which CVM responded to disasters in 2008. The CVM response to the floods early 2008, followed by a cyclone (Jokwe) in March, demonstrated the increased capacity reached by the NS in dealing with natural disasters of a scale that in the past would have prompted external support (in the form of FACT, ERUs, etc.).  CVM managed to assist some 9,000 families with complete packs of relief items, and provided first aid, water and sanitation, shelter and relief support to the people they targeted. In May 2008, CVM was also involved in providing shelter, first aid and psycho-social support to the 40,000 Mozambicans who returned to the country after the Xenophobic attacks in South Africa.

2. This increased capacity is also the result of follow-up training organised for CVM through Spanish RC after the Relief ERU deployment of 2007, and the participation of CVM staff to the Global Relief Training held in Geneva in April, 2008. Both Relief ERU courses in Spain (October 2007 and September 2008) had representatives from the CVM coming to Spain to meet RC/RC participants from several countries while contributing first-hand field experience to the course.  Also, to further strengthen the linkage between deploying and receiving National Societies, Spanish RC sent two delegates to support the deployment of CVM water and sanitation staff to support the floods operation of 2008. In 2009 this was followed-up by Madrid, which sent 2 more delegates to check the state of the used water and sanitation equipment and gave additional ERU training in February 2009.
3. It appears however that some capacity gaps exist at district level, in terms of logistic capacity / lack of relief items for first response, lack of volunteer basic equipment and kits, lack of transport means, etc. This can be linked to the broader issues of resourcing at branch level. It is assumed that the DM Master Plan developed by CVM addresses these issues accordingly. Possibly a revision of the national stock pre-positioning strategy should be undertaken.  As for volunteer equipment, it needs to be brought to a sufficient level not to undermine the volunteer response capacity and motivation – a more strategic use of DREF for this purpose should be considered in the future.
4. The national society strives at learning from its experience in disaster response. An evaluation / final report of the 2007 floods and cyclone operation has just been released by CVM in Portuguese, and a comparison study of CVM response to disasters in 2007 and 2008 has been conducted. However, according to SGS benchmarking audit, CVM should establish better PMER systems in order to demonstrate real impact of their programs (similar issues addressed under section DP/DRR).

	Recommendations
	Who

	Disaster Response capacity
	

	While recognising the logistics capacity gaps mentioned above, to have stocks pre-positioned at district level might not be the most appropriate and cost-effective solution for CVM. Other measures appear to be in place to meet larger needs such as MoU among NSs from the region to use stocks across borders, contingency stock held by the government and other agencies, as reflected in the contingency plans. The Zone should support CVM to develop the most appropriate stock pre-positioning and supply strategy at national level. Contingency plans should clearly reflect available capacity according to identified disaster scenarios.
	Zone / National

	It is also recommended to use DREF more strategically in order to systematically replenish national stocks and bring volunteer response capacity to an acceptable level after each operation.
	National

	Considering that the region often requires use of regional and international surge capacity tools such as RDRT, FACT and ERUs, it is recommended that continuous exposure to training and refresher courses is provided to the Zone and NSs staff.
	Zone / Global


Early Warning / Information management
Assess level of coordination, information / knowledge management and analysis in support of disaster response

Criteria

Regional/Zone level

· IFRC ensures effective dissemination of alerts, monitoring information etc…

· IFRC ensures/supports effective coordination with other organizations, inter-agency coordination and coordination of disaster response tools when deployed (RDRT, FACT, ERU)
1. The SA Zone promotes and makes use of Federation platforms (ex. DMIS) to disseminate alerts and operational information, activate their response systems, and submit DREF requests on behalf of National Societies. Cooperation with climate organizations regionally as well as with the climate centre in the Netherlands is active, in particular to monitor changing climate patterns.
2. Coordination is ensured with external partners through bi-weekly meetings with the regional inter-agency coordination body led by OCHA, attended by most UN agencies, NGOs, etc.

National level

· Early warning systems (national or community-based), including DMIS, are accessible to NS & rapid response mechanisms are in place

· RC Early warning capacity built at the national, intermediary and local levels. Use of national data/forecasting models to inform activity planning in this regard

· Early warning / early action partnerships are developed

· The position of the NS in the National (government) DM plan

· Use of effective information & communication procedures

1. In Mozambique, emphasis is reportedly on community-based preparedness activities for cyclones and floods, community-based early warning system, community response capacity, evacuation plans, establishment and training of local DM committees and rescue teams, and awareness raising campaigns. The visit to the communities suggested that established EW systems were still in place, and that regular simulation exercises with the communities were run by the RC volunteers. However, some training and financial resources should be provided by CVM in order to ensure maintenance of the material provided (bicycles, etc.).  
2. The relationship of CVM with INGC (National Institute for Disaster Management) is active both in disaster response and disaster preparedness. In times of emergency CVM complements the INGC capacity with its own DM committees and volunteers, which outreach to the community level, is valued by all partners. CVM role is identified in the national and provincial contingency plan, whereby the NS material and human resource capacity is accounted for. However, the meeting held with INGC at provincial level, in Xai Xai, where the representative had been in place for about a year, demonstrated a lack of understanding of the specific role of the Red Cross and its added value in comparison with other NGOs. This episode is clearly not representative of the good relationship that CVM has with the authorities at national level (for instance the authorities have been involved in the VCA multi-sector exercise, thus sharing the same analysis of risks, capacities and vulnerabilities in the most disaster-prone areas, and conducted joint training and simulation exercises), but indicates the need for a constant dialogue with INGC at all levels (province, district) to promote a common understanding of roles and responsibilities across the institutions.
WASH, Shelter and Recovery

Assess level of capacity to design and deliver quality post-disaster recovery programmes, as well as appropriate WASH and sheltering programmes

Criteria

Regional/Zone level

· DM staff and NS are aware of IFRC responsibilities in shelter

· Regional Emergency Appeals contain plans of actions based on properly assessed needs and considering recovery measures, possibly based on post-disaster recovery guidelines 
· Pool of regionally trained recovery personnel available for deployment
· Appropriate WASH capacity- in terms of trained personnel and available equipment and supplies -  to respond to regional disaster events 

1. Hosting of a shelter kit regional training is currently under discussion with the Zone office. This technical training aims at providing NSs with sheltering solutions (also through the use of shelter kits) that go beyond the provision of tents and tarpaulins, and builds on the use of traditional materials, with emphasis on improved and water-resistant techniques.
2. Water and Sanitation in emergency is being improved through the pre-positioning of kits (10 000 kits are currently available in 4 countries of the region), usually deployed in response to floods operations and for the use of which, training was provided regionally to water and sanitation staff, and DM staff trained in RDRT and other technical areas. Important to mention the link to health and care, especially in relation to education and hygiene dissemination, which was clearly highlighted by the Health Coordinator at the Zone.
3. Further technical assistance to NSs from the region, both from the Zone and Geneva-based technical experts, was provided through:
· Participation from Zimbabwe RC in global livelihoods guidelines development workshop in Sri Lanka in November 2008

· Recovery technical review and appraisal of the Zimbabwe Emergency Appeals 

· Relief technical support for the Mozambique and Zimbabwe emergency appeals.

National level

· NS develops appropriate action plans for community-focused recovery

· NS has sufficient staff/volunteers trained in shelter, particularly in the use of shelter kits, and in recovery

· NS has sufficient staff/volunteers trained in the use of water and sanitation emergency response kits as well as in hygiene promotion

· NS has sufficient policy guidance, tools, standard operating procedures 

1. CVM expressed clear needs for increased technical assistance in several sectors (i.e. logistics, water and sanitation, relief and shelter coordination). This could be addressed by encouraging a regional peer-to-peer support and could be facilitated by maintaining a regional database of NS resources available for cross-use. Said that, technical support for recovery assessment following Cyclone Jokwe was provided to CVM in June 2008, as well as in relief as already mentioned above.
2. As already mentioned, two representatives from CVM participated in the global Shelter Technical Training hosted by the Spanish Red Cross in Barcelona in March 2009. On shelter cluster coordination, the recent handover from UN Habitat to Mozambique Red Cross for the lead of shelter recovery phase will require further support for the national society to take over the lead of the shelter cluster contingency planning and preparedness component.  The “cluster” system is now a permanent coordination mechanism in Mozambique and this coordination role is seen by the NS as a very challenging task which would require further technical expertise and assistance.  CMV is currently waiting for the appointment of a UN volunteer who will train one of their staff on cluster coordination, but there seemed to be expectations from the NS that such assistance should come from the Zone or Global Shelter department. 
3. With regard to water & sanitation in emergency, the first Water & Sanitation Kits technical training was undertaken in Namibia in November 2008. The Mozambique RC was invited but did not have someone available to attend. The next training is planned within the next two months in Harare. Despite that, Mozambique Red Cross is aware of Water & Sanitation Kit availability and use, and would prefer their deployment instead of global tools, unless in the event of major disaster response.
	Recommendations
	Who

	Technical assistance and global matters
	

	There appears to be confusion about the role of the Federation in the shelter cluster. In Mozambique, the “cluster” system is more of a national/permanent sector coordination mechanism which has to be dealt with at national level. Recognising that  acceptance by CVM to take over a coordinating role from UN habitat is a national choice, it is however expected that the Federation Secretariat would provide adequate support to CVM to lead the country level shelter cluster contingency planning. It is recommended to seek clarity from the Zone and Global shelter department to address expectations at national level. 
	Global / Zone / National


	Technical assistance in WASH and Shelter seemed to be more “hardware” oriented (kit pre-positioning) than focused on “soft” skill development. It is recommended that future monitoring and programme reports clearly highlight the integration between the two elements.
	Global / Zone

	Despite the fact that the monitoring team limited the review scope to disaster management, the areas explored are still found too broad to allow a clear understanding of how the capacity building investments have had an impact nationally and regionally. The next evaluation should therefore be more focused and possibly develop longitudinal country case studies to monitor more deeply the flow of capacity building within the organisation. For further discussion at DFID and DG ECHO review meetings.
	Global (PMER) / donors


Acknowledgements

The team would like to thank the CVM Secretary General, Fernanda Teixeira, the national society staff and volunteers who have so honestly and transparently shared information with the monitoring team. The team is also grateful for the cross-sector meetings held in Johannesburg at the Zone office. Special thanks are due to Farid Aiywar, Zone Disaster Management Coordinator and Martin Acosta, Federation Representative in Maputo, for the facilitation and logistical support they have provided to the team.

Annexes (available on request)
· Terms of Reference

· List of documents provided as preparatory reading

· Agenda for the visit in Johannesburg

· Agenda for the visit in Mozambique

· Presentation “Mozambique Red Cross: a profile of a National Society” 
· Presentation “Mozambique Red Cross: Disasters 2008” 
List of acronyms and abbreviations

CVM: Cruz Vermelha de Moçambique (Mozambique Red Cross)

DFID: Department for International Development

DG ECHO: Directorate General for Humanitarian Aid – European Commission

DM: Disaster management

DMIS: Disaster Management Information System

DP: Disaster preparedness

DREF: Disaster Relief Emergency Fund

DRR: Disaster risk reduction

ERU: Emergency Response Units

EW: Early Warning

FACT: Field Assessment and Coordination Teams

HES: Household Economic Security

IDRL: International Disaster Response Law

IFRC: International Federation of Red Cross and Red Crescent Societies

INGC: National Disaster Management Institute
JMM: Joint Monitoring Mission (team)

MDG: Millennium Development Goal

MoH: Ministry of Health

MSM: Mass Sanitation Module

NDRT: National Disaster Response Teams

NS: National Society

OD: Organisational Development

P&V: Principles and Values

PMER: Planning, Monitoring, Evaluation and Reporting

PNS: Participating National Society

PSEXA: Prevention of Sexual Abuse

RDRT: Regional Disaster Response Teams

RLU: Regional Logistics Unit

VCA: Vulnerability Capacity Assessment

WASH: Water, Sanitation and Hygiene

WPNS: Well Prepared National Societies

� The Capacity Building programme covers approx. 7.5% of the Federation global/zone/country DM annual budget in 2009 (DG ECHO contribution is EUR 4.5 million for 18 months); The DFID IS III annual allocation (GBP 5.06 million) covers approx. 10.5% of the Federation global/zone/country annual DM budget in 2009.





� Many of the reported findings / statements made in this report are based on existing documents that will be referenced as footnotes for back up.


� See the “Zambesi River initiative” for effective use of both VCA and WPNS. WPNS in particular was helpful in assessing branch capacities. 


Link:  �HYPERLINK "http://www.ifrc.org/Docs/pubs/disasters/160400-Zambezi_River_Project_LR3.pdf"�http://www.ifrc.org/Docs/pubs/disasters/160400-Zambezi_River_Project_LR3.pdf�


See also the Annual Report 2008 for use of VCA and WPNS:


 http://www.ifrc.org/docs/appeals/annual08/MAA6300108ar.pdf


Results of WPNS process for Mozambique RC were also part of the documents reviewed for this mission.





� DM Coordinator statement. See also Zambesi river initiative / operational plans :


 �HYPERLINK "http://www.ifrc.org/Docs/pubs/disasters/160400-Zambezi_River_Project_LR3.pdf"�http://www.ifrc.org/Docs/pubs/disasters/160400-Zambezi_River_Project_LR3.pdf�


and Southern Africa Zone Plan for 2009/10: �HYPERLINK "http://www.ifrc.org/docs/appeals/annual09/MAA6300109p.pdf"�http://www.ifrc.org/docs/appeals/annual09/MAA6300109p.pdf�





� RDRT training is conducted bi-annually (see SA Zone Plan 09/10) and support is provided to NS to build their NDRT. According to the SAZO Annual Report 2008, quote “In terms of capacity building, the DM unit enhanced disaster response skills through training and refresher courses for RDRT members. In addition, the unit effectively co-ordinated a functional taskforce that was instrumental in developing contingency plans for recurrent disasters. Two planning and review meetings were held in Johannesburg, attended by all National Society DM officers, to evaluate the progress on implementation against the planned activities, and to plan for 2009. The DM officers developed an accountability framework between SAZO and the National Societies that will ensure closer monitoring of progress against targets and goals set over the short-, medium- and long-term.” See link: http://www.ifrc.org/docs/appeals/annual08/MAA6300108ar.pdf


� See “CVM: a national society profile” Power-Point presentation in annex


� This was reported but not observed by the team. In fact shelter expertise within CVM was not demonstrated during the mission.


� Section E. of WPNS profile of CVM, as well as CVM power-point presentation.


� See reported information in the CVM power-point presentation « Disasters 2008 », in annex. Final report of the flood and cyclone intervention only available in Portuguese.


� Information sharing with Geneva is ensured through Zone monthly reports. Quarterly coordination meetings with external partners (including PNSs) are organised by the Zone





